EASP

Enterprise AI Security Platform

Team Implementation Task Book v1.0

Planning and ownership artifact — not an authorization to begin coding

Technical Project Manager & Senior System Architect role

10-person team — Cybersecurity, AI/Data Science, Computer Science

0. How to Read This Document

This Task Book is a planning and ownership artifact only. No phase beyond Phase 0 is authorized to begin by the existence of this document. The academic/project documents — EASP Chapter 1 Final v2.0 and the (currently unavailable) AI Subsystem Proposal and SRS v2.1 — define the approved architecture and remain the source of truth. EASP_fixed.ipynb provides implementation evidence and prototype code, not an approved specification. Where the notebook and the academic documentation disagree, that disagreement is flagged explicitly below rather than silently resolved.

Documents used

| Document | Role |
| --- | --- |
| EASP Chapter 1 Final v2.0 (.docx) | Authoritative academic baseline: scope, architecture, model rules, dataset list |
| AI Subsystem Proposal and SRS v2.1 | Referenced by Chapter 1 but not supplied to this session — endpoint-level and latency-per-stage detail from it remains unverified |
| EASP_fixed.ipynb | Implementation evidence / prototype code — mined for the Notebook-to-Production Migration Matrix below |
| EASP Implementation Readiness Audit & Roadmap.md (prior session) | Prior planning artifact; reconciled with this Task Book's 15-phase structure below where the two differ |

Reconciliation note: an earlier planning session produced a 24-phase roadmap. This Task Book uses the 15-phase structure (Phase 0-14) specified for this deliverable. The 24-phase document's technical content (database schema, API versioning, risk-fusion rationale) remains valid and is folded into the phases below; only the phase numbering and granularity differ.

1. Team Structure

| Track | Members | Primary Ownership |
| --- | --- | --- |
| Cybersecurity | Cyber 1, Cyber 2, Cyber 3, Cyber 4 | Auth/RBAC, DLP/redaction, Risk/Policy engine, Security testing/audit |
| AI / Data Science | AI 1, AI 2, AI 3, AI 4 | RawNet2, Faster-Whisper, mBERT+head, AI integration/FastAPI |
| Computer Science | CS 1, CS 2 | Backend/Express/API integration, Frontend/React/MongoDB/DevOps |

Person-to-component map

| Person | Owns |
| --- | --- |
| Cyber 1(attia) | Authentication, JWT, RBAC |
| Cyber 2(sayed) | DLP, Data Security, Redaction |
| Cyber 3(moaz) | Risk Engine, Policy Engine |
| Cyber 4(kareem) | Security Testing, Audit Security |
| AI 1(Abrar) | RawNet2, Voice Deepfake Detection |
| AI 2(Basmalla) | Faster-Whisper, Speech-to-Text |
| AI 3(Andewer) | mBERT, Classification Head, Social Engineering |
| AI 4(kareem) | AI Integration, FastAPI, Data Science Integration |
| CS 1(maram) | Backend, Express, APIs, Integration |
| CS 2(allam) | Frontend, React, MongoDB, Docker/DevOps |

2. Current Project Scope

Baseline (mandatory)

Authentication/JWT/RBAC · API Gateway · DLP (Regex, Presidio, spaCy) · Reversible encrypted token mapping · Voice deepfake detection (RawNet2) · Faster-Whisper · mBERT + classification head · Phase 1 rule-based Risk Engine · Policy Engine · Audit Logging · Security Dashboard · Controlled audio/voice environment · Security testing.

Conditional / Should-Implement

XGBoost + SHAP · Browser extension (2-3 selected AI applications) · SIEM export · confidence calibration.

Future Work — excluded from every phase below

Image/video deepfake detection · production PBX · universal HTTPS interception · Threat Intelligence · voiceprint verification · federated learning · autoencoder anomaly detection.

3. Git / Team Workflow

Branch model: main <- develop <- feature/<component>. No direct uncontrolled changes to main.

| Rule | Detail |
| --- | --- |
| Branch per task | feature/<component>, e.g. feature/dlp-engine, feature/rawnet2-service |
| Ownership | Every task has one named owner (see Person-by-Person Task List, Section 8) |
| Merge path | feature/* -> develop (peer review required) -> main (integration checkpoints only, e.g. end of Phase 12) |
| Quality gate | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT. A task is not complete because code was merely written. |
| Git checkpoint tags | phase-00-foundation, phase-01-auth-rbac, ... phase-14-final-demo (one per phase, applied to develop after that phase's acceptance criteria pass) |