EASP

Enterprise AI Security Platform

Team Implementation Task Book v1.0

Planning and ownership artifact — not an authorization to begin coding

Technical Project Manager & Senior System Architect role

10-person team — Cybersecurity, AI/Data Science, Computer Science

# 0. How to Read This Document

This Task Book is a planning and ownership artifact only. No phase beyond Phase 0 is authorized to begin by the existence of this document. The academic/project documents — EASP Chapter 1 Final v2.0 and the (currently unavailable) AI Subsystem Proposal and SRS v2.1 — define the approved architecture and remain the source of truth. EASP_fixed.ipynb provides implementation evidence and prototype code, not an approved specification. Where the notebook and the academic documentation disagree, that disagreement is flagged explicitly below rather than silently resolved.

### Documents used

| Document | Role |
| --- | --- |
| EASP Chapter 1 Final v2.0 (.docx) | Authoritative academic baseline: scope, architecture, model rules, dataset list |
| AI Subsystem Proposal and SRS v2.1 | Referenced by Chapter 1 but not supplied to this session — endpoint-level and latency-per-stage detail from it remains unverified |
| EASP_fixed.ipynb | Implementation evidence / prototype code — mined for the Notebook-to-Production Migration Matrix below |
| EASP Implementation Readiness Audit & Roadmap.md (prior session) | Prior planning artifact; reconciled with this Task Book's 15-phase structure below where the two differ |

Reconciliation note: an earlier planning session produced a 24-phase roadmap. This Task Book uses the 15-phase structure (Phase 0-14) specified for this deliverable. The 24-phase document's technical content (database schema, API versioning, risk-fusion rationale) remains valid and is folded into the phases below; only the phase numbering and granularity differ.

# 1. Team Structure

| Track | Members | Primary Ownership |
| --- | --- | --- |
| Cybersecurity | Cyber 1, Cyber 2, Cyber 3, Cyber 4 | Auth/RBAC, DLP/redaction, Risk/Policy engine, Security testing/audit |
| AI / Data Science | AI 1, AI 2, AI 3, AI 4 | RawNet2, Faster-Whisper, mBERT+head, AI integration/FastAPI |
| Computer Science | CS 1, CS 2 | Backend/Express/API integration, Frontend/React/MongoDB/DevOps |

### Person-to-component map

| Person | Owns |
| --- | --- |
| Cyber 1 | Authentication, JWT, RBAC |
| Cyber 2 | DLP, Data Security, Redaction |
| Cyber 3 | Risk Engine, Policy Engine |
| Cyber 4 | Security Testing, Audit Security |
| AI 1 | RawNet2, Voice Deepfake Detection |
| AI 2 | Faster-Whisper, Speech-to-Text |
| AI 3 | mBERT, Classification Head, Social Engineering |
| AI 4 | AI Integration, FastAPI, Data Science Integration |
| CS 1 | Backend, Express, APIs, Integration |
| CS 2 | Frontend, React, MongoDB, Docker/DevOps |

# 2. Current Project Scope

### Baseline (mandatory)

Authentication/JWT/RBAC · API Gateway · DLP (Regex, Presidio, spaCy) · Reversible encrypted token mapping · Voice deepfake detection (RawNet2) · Faster-Whisper · mBERT + classification head · Phase 1 rule-based Risk Engine · Policy Engine · Audit Logging · Security Dashboard · Controlled audio/voice environment · Security testing.

### Conditional / Should-Implement

XGBoost + SHAP · Browser extension (2-3 selected AI applications) · SIEM export · confidence calibration.

### Future Work — excluded from every phase below

Image/video deepfake detection · production PBX · universal HTTPS interception · Threat Intelligence · voiceprint verification · federated learning · autoencoder anomaly detection.

# 3. Git / Team Workflow

Branch model: main <- develop <- feature/<component>. No direct uncontrolled changes to main.

| Rule | Detail |
| --- | --- |
| Branch per task | feature/<component>, e.g. feature/dlp-engine, feature/rawnet2-service |
| Ownership | Every task has one named owner (see Person-by-Person Task List, Section 8) |
| Merge path | feature/* -> develop (peer review required) -> main (integration checkpoints only, e.g. end of Phase 12) |
| Quality gate | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT. A task is not complete because code was merely written. |
| Git checkpoint tags | phase-00-foundation, phase-01-auth-rbac, ... phase-14-final-demo (one per phase, applied to develop after that phase's acceptance criteria pass) |

# 4. Notebook Analysis — Migration Matrix

EASP_fixed.ipynb (19 cells) was inspected component-by-component. The notebook already contains its own self-review comments (marked FIX/ADDED in the source) flagging several of the issues below — this matrix formalizes them as an ownership and status record rather than discovering them fresh.

| Notebook Component | Production Destination | Owner | Phase | Status |
| --- | --- | --- | --- | --- |
| DLP engine (Regex + Presidio + spaCy, ReversibleDLPEngine) | ai-services/dlp-service/ (Phase 3) + reversible-redaction module (Phase 4) | Cyber 2 / AI 4 | 3-4 | Portable as-is; verify recognizer coverage against real PII test set before reuse |
| Custom API-key PatternRecognizer | ai-services/dlp-service/recognizers.py | AI 4 | 3 | Portable; the notebook's own demo key value must be replaced with a clearly-synthetic fixture, never reused literally |
| Reversible redaction / token restore (Fernet) | backend/src/models/TokenMapping.js + redaction.py | Cyber 2 | 4 | Logic portable; key management must move to KMS/secret manager per the notebook's own Cell 12 warning |
| mBERT encoder + classification head | ai-services/social-engineering-service/model.py | AI 3 | 9 | Portable; head is untrained until Phase 9's training loop runs on the team's own split |
| Training loop (class-weighted BCEWithLogitsLoss, pos_weight) | ai-services/social-engineering-service/train.py | AI 3 | 9 | Portable; verify pos_weight recomputed on the team's actual train split, not reused from the notebook run |
| Label mapping (SMS Spam Collection -> 4 multi-labels via regex) | ai-services/social-engineering-service/label_mapping.py | AI 3 | 9 | Portable, but this is a heuristic proxy label, not ground truth — document as such |
| Evaluation (per-label precision/recall/F1) | tests/ai-evaluation/ (Phase 13), prototyped in Phase 9 | AI 3 | 9 / 13 | Portable methodology; numbers must be re-run on the team's own split, not copied from the notebook |
| RawNet2 architecture (SincConv, FMS, ResBlock, RawNet2) | ai-services/voice-deepfake-service/rawnet2.py | AI 1 | 8 | Portable as-is (standard architecture) |
| RawNet2VoiceDetector (checkpoint loading) | ai-services/voice-deepfake-service/main.py | AI 1 | 8 | Portable; requires a real ASVspoof-trained checkpoint, not the notebook's placeholder path |
| DummyVoiceDetector (random-score fallback) | NOT ported to production | AI 1 | 8 | Do not migrate — production must fail loudly on missing weights, never silently return random scores |
| Faster-Whisper SpeechTranscriber | ai-services/whisper-service/main.py | AI 2 | 7 | Portable as-is (pretrained, no fine-tuning) |
| AudioProcessor (preprocessing) | ai-services/whisper-service/audio_processor.py | AI 2 | 7 | Portable as-is |
| UnifiedRiskEngine (Phase 1 rule-based fusion) | backend/src/services/riskEngine.js | Cyber 3 | 6 | Logic portable, but weights (0.40/0.35/0.25) and BLOCK threshold (0.70) are NOT approved values — flag for team/supervisor sign-off before adoption |
| Phase 2 ML Risk Engine (XGBoost + SHAP) | Not built in the 15-phase baseline; conditional follow-on after Phase 13's go/no-go | AI 4 | 13 (decision only) | Notebook's training data is fully synthetic and circular (labels generated from the same weighted-sum rule the model is meant to learn) — must not be treated as a working model until trained on real analyst-labeled incidents |
| FastAPI microservice (EASP_AIService + 3 endpoints) | ai-services/ai-gateway/ (or consolidated entrypoint) | AI 4 | 10 | The class/wrapper logic is portable; the notebook itself notes an earlier version defined the class but never actually served it over HTTP — verify the production version is genuinely reachable |
| Latency benchmarking harness | tests/ai-evaluation/latency (Phase 13), prototyped Phase 7 | CS 1 | 7 / 13 | Methodology portable; notebook numbers are dev-machine, not representative — re-measure in the actual deployment environment |
| Voice deepfake evaluation (ASVspoof-style EER/ROC-AUC) | tests/ai-evaluation/voice-eer (Phase 13) | AI 1 | 8 / 13 | SIMULATED — notebook Cell 14 generates bonafide/spoofed scores from np.random.normal, not a real model run. Must be re-run for real before any number is reported |
| Model artifact saving (torch.save, xgboost save_model) | easp_ai_artifacts/ (per-service, Phases 9/10) | AI 3 / AI 4 | 9 / 10 | Portable pattern; notebook already correctly excludes the Fernet key from this save path — preserve that separation |
| Live voice recording / dummy audio generation | NOT ported — test fixtures only | AI 1 / QA | 7-8 (test fixtures) | The notebook's np.random-generated dummy_audio is a smoke-test fixture, not a data source; production testing needs real controlled-environment recordings |

## 4.1 Explicit Flags

- Simulated RawNet2 evaluation: notebook Cell 14 computes EER/ROC-AUC from np.random.normal-generated bonafide/spoofed score distributions, not a real model run. Never quote these numbers as measured accuracy.

- Synthetic XGBoost data: notebook Cell 9's Phase 2 risk model trains on np.random-generated features and rule-derived labels (circular — the model would just relearn UnifiedRiskEngine's own formula). Falls back to this only when real_security_incidents.csv is absent.

- Synthetic risk labels: same as above — the fallback labels are generated from the identical weighted-sum formula used in Phase 1, so a model trained on them adds no real value.

- Hardcoded demo values: dummy_audio (Cell 1, random waveform for smoke-testing only), simulated_deepfake_score = 0.85 (Cell 4, a worked-example constant, not a measurement).

- Hardcoded thresholds: Cell 4's weights (voice_deepfake 0.40 / social_engineering 0.35 / dlp_sensitivity 0.25) and BLOCK threshold (total_risk >= 0.70) are not present or approved in Chapter 1 Final v2.0, which states thresholds are 'to be defined during implementation.' These are a reasonable prototype starting point, not an approved baseline — flagged for sign-off at Phase 6.

- Temporary credentials/secrets: Cell 4's worked example embeds a realistic-looking but fake AWS key string in a demo prompt. Must not be reused verbatim as a production test fixture. Cell 12 explicitly (and correctly) warns that the DLP engine's Fernet encryption key must never be persisted alongside model artifacts.

- Notebook-only dependencies: runtime spaCy model download (en_core_web_lg), a commented-out uvicorn.run() invocation (the FastAPI app is defined but never actually served inside the notebook), and in-memory-only key handling that has no persistence story outside the notebook session.

# 5. AI / Data Science Dataset Plan

Dataset work starts in Phase 0, in parallel with backend/cybersecurity scaffolding — it does not wait for the AI implementation phases (7-9).

| Dataset | Type | Used By | Notes |
| --- | --- | --- | --- |
| ASVspoof 2019/2021 | Real / Public | RawNet2 evaluation (Phase 8, 13) | Not for training — pretrained checkpoint is baseline; fine-tuning optional |
| WaveFake | Real / Public | RawNet2 secondary evaluation (Phase 8, 13) | Supplementary spoofed-speech benchmark |
| SMS Spam Collection | Real / Public | mBERT+head training via regex proxy-labels (Phase 9) | Labels are heuristic (regex-derived), not hand-annotated for social engineering |
| Enron Email | Real / Public | Documented alternate/supplementary corpus for social-engineering/phishing patterns (Phase 9) | Not used directly in notebook Cell 6's pipeline; available if the team extends labeling |
| Public phishing corpora | Real / Public | Supplementary social-engineering signal source (Phase 9) | Source and licensing to be finalized in Phase 0's DATASETS.md |
| Synthetic scripted call dialogues | Team-Generated Synthetic | Controlled-environment demo scenarios (Phase 7-9, 12, 14) | For the audio/VoIP demonstration environment, not for training claims |
| ai4privacy/pii-masking-200k | Real / Public | DLP evaluation sample (Phase 3, 13) | Evaluation only — Presidio/spaCy are pretrained, not trained on this set |
| CoNLL-2003 | Real / Public | spaCy/NER-adjacent reference benchmark (Phase 3) | Reference/validation use for the NER component |
| Synthetic risk incidents | Team-Generated Synthetic | Notebook Cell 9's XGBoost placeholder training data | FLAGGED: currently circular (labels derived from the same rule the model would learn) — not usable for a real Phase 2 model until replaced with real analyst-labeled incidents |

### Data preparation track (parallel to Phase 0-9)

- Dataset acquisition and licensing verification — owned by AI 4, tracked in DATASETS.md from Phase 0

- Cleaning, preprocessing, train/validation/test split — per-component, owned by AI 1 (RawNet2), AI 2 (Whisper — pretrained, minimal prep), AI 3 (mBERT+head)

- Label definition — AI 3 for social-engineering multi-labels; Cyber 2 for DLP entity categories

- Synthetic data creation — clearly separated from real data at every step (see Section 5 table's Type column); synthetic risk incidents are explicitly not usable for a reportable Phase 2 model until replaced with real analyst-labeled data

- Leakage prevention — train/test split performed before any label-derivation heuristic is tuned, to avoid tuning regex rules against the test set

- Evaluation datasets — ASVspoof (RawNet2), held-out SMS Spam split (mBERT), ai4privacy sample (DLP) — all real/public, none team-generated

# 6. Phase-by-Phase Task Breakdown

Each phase follows: IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT. No phase begins until the previous phase's acceptance criteria are met.

## PHASE 0 — Foundation

| 1. Objective | Establish the monorepo skeleton, tooling, environment baseline, and parallel Data Preparation track. No business logic is written. |
| --- | --- |
| 2. Why this phase exists | Every later phase assumes a runnable repo, agreed folder structure, and a Git branching model. Dataset work (Section: Data Science Rule) must also start here rather than waiting for Phase 9/10, since AI phases need labeled data ready when they begin. |
| 3. Prerequisites | • Team confirms monorepo structure below • Team confirms Docker/docker-compose for Python AI services • GitHub repo created with main/develop branches |
| 7. Responsible person(s) | CS 1 (lead), all members (setup buy-in) |
| 8. Deliverables | • Empty-but-runnable repo skeleton • .gitignore • README.md • DATASETS.md stub • Git branch policy documented |
| 9. Files / components | • EASP/backend/ • EASP/frontend/ • EASP/ai-services/ • EASP/data/{raw,processed,evaluation} • EASP/docs/ • EASP/tests/ • EASP/docker/ • README.md • .gitignore • .env.example |
| 10. APIs required | • None |
| 11. Database changes | • None |
| 12. Dataset requirements | No modeling yet. Start licensing checks and download-availability checks for all 9 documented datasets (see Dataset Plan). |
| 13. Integration points | • None yet — this phase produces the container all other phases build into |
| 14. Testing requirements | • Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding • docker-compose up boots empty stub services without error |
| 15. Acceptance criteria | • Repo clones clean on a fresh machine • Folder structure matches the agreed layout • No secrets committed (verified with a secret scanner) • DATASETS.md lists all 9 datasets with licensing status |
| 16. Definition of Done | IMPLEMENT (scaffold) -> RUN (docker-compose up) -> TEST (lint/smoke) -> FIX -> VERIFY (2nd teammate clones and boots) -> DOCUMENT (README) -> COMMIT to develop. |
| 17. Dependencies | • None |
| 18. Risks | • Team disagreement on monorepo vs multi-repo stalls Phase 0 — Mitigation: Decide by vote in kickoff meeting; monorepo is the default recommendation for a 10-person student team |
| 19. Do NOT implement here | • Any authentication, DLP, or AI logic • Any real dataset download beyond licensing checks |

### Phase 0 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P00-001 | P0 | Cyber | Cyber 4 | Set up .env.example with no real secrets + secret-scanning note in README | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |
| T-P00-002 | P0 | AI | AI 4 | Create data/raw, data/processed, data/evaluation folders + DATASETS.md tracking sheet | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |
| T-P00-003 | P0 | AI | AI 4 | Begin licensing verification for ASVspoof 2019/2021, WaveFake, SMS Spam Collection, Enron Email, ai4privacy/pii-masking-200k, CoNLL-2003 | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |
| T-P00-004 | P0 | CS | CS 1 | Scaffold backend/, frontend/, ai-services/, data/, docs/, tests/, docker/ folders | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |
| T-P00-005 | P0 | CS | CS 2 | Configure linting/formatting (ESLint/Prettier for JS, black/flake8 for Python) | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |
| T-P00-006 | P0 | CS | CS 2 | Set up docker-compose skeleton (empty service stubs) | Team confirms monorepo structure below | Empty-but-runnable repo skeleton | None | Smoke test: npm run lint and python -m py_compile succeed on empty scaffolding | Repo clones clean on a fresh machine |

## PHASE 1 — Authentication + JWT + RBAC

| 1. Objective | Working login/registration, JWT issuance, bcrypt password hashing, and role-based middleware (Employee / Analyst / Administrator). |
| --- | --- |
| 2. Why this phase exists | Every protected route in every later phase (DLP scan, dashboard, audit log) depends on an authenticated, role-tagged request context. |
| 3. Prerequisites | • Phase 0 complete • MongoDB instance available (local or Atlas) |
| 7. Responsible person(s) | Cyber 1 (lead), CS 1 (backend wiring), CS 2 (frontend) |
| 8. Deliverables | • Working login/registration flow • JWT issuance + verification middleware • RBAC middleware • Seeded roles collection |
| 9. Files / components | • backend/src/controllers/authController.js • backend/src/middleware/auth.js • backend/src/middleware/rbac.js • backend/src/routes/authRoutes.js • backend/src/models/User.js • backend/src/models/Role.js • frontend/src/pages/Login.jsx |
| 10. APIs required | • POST /api/v1/auth/register • POST /api/v1/auth/login -> JWT • GET /api/v1/auth/me (protected) |
| 11. Database changes | • Creates users, roles collections; seeds Employee/Analyst/Administrator roles |
| 12. Dataset requirements | None. (Data Prep track continues in parallel per Phase 0.) |
| 13. Integration points | • Frontend login screen -> auth API • auth middleware becomes the dependency of every route added from Phase 2 onward |
| 14. Testing requirements | • Valid login • invalid password • expired token • missing token • wrong-role access attempt — each as an explicit documented test case |
| 15. Acceptance criteria | • All 5 test cases above pass • No plaintext password ever logged or stored • RBAC blocks a non-admin from an admin-only stub route |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST (5 cases) -> FIX -> VERIFY (Cyber 4 reviews) -> DOCUMENT (API contract in docs/) -> COMMIT to feature/auth-rbac, merge to develop. |
| 17. Dependencies | • Phase 0 |
| 18. Risks | • JWT secret accidentally committed — Mitigation: Enforce .env + secret-scan pre-commit hook from Phase 0 |
| 19. Do NOT implement here | • API Gateway rate limiting (Phase 2) • Audit logging of auth events (Phase 5) |

### Phase 1 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P01-007 | P1 | Cyber | Cyber 1 | Design JWT claims (userId, role, exp) and short-TTL/refresh strategy | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |
| T-P01-008 | P1 | Cyber | Cyber 1 | Implement bcrypt hashing (>=12 salt rounds), never log plaintext passwords | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |
| T-P01-009 | P1 | Cyber | Cyber 1 | Implement RBAC middleware enforcing Employee/Analyst/Administrator | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |
| T-P01-010 | P1 | CS | CS 1 | Mongoose User/Role schemas + seed default roles | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |
| T-P01-011 | P1 | CS | CS 1 | Auth routes: POST /api/v1/auth/register, /login, GET /auth/me | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |
| T-P01-012 | P1 | CS | CS 2 | React login/register screens wired to the auth API | Phase 0 complete | Working login/registration flow | Phase 0 | Valid login | All 5 test cases above pass |

## PHASE 2 — API Gateway + Security Middleware

| 1. Objective | Central request pipeline in front of every route: rate limiting, input validation, security headers, CORS allow-list, request-logging hook. |
| --- | --- |
| 2. Why this phase exists | Every subsequent service (DLP, risk, dashboard) is exposed through this gateway layer; building it before those services means they inherit protection by default instead of bolting it on later. |
| 3. Prerequisites | • Phase 1 complete (auth middleware exists to sit behind the gateway) |
| 7. Responsible person(s) | Cyber 1 (lead), Cyber 4 (headers/testing), CS 1 (wiring) |
| 8. Deliverables | • Rate-limit middleware • Validation middleware • Finalized security-header/CORS config |
| 9. Files / components | • backend/src/middleware/rateLimit.js • backend/src/middleware/validate.js • backend/src/middleware/securityHeaders.js |
| 10. APIs required | • No new public endpoints — wraps existing ones |
| 11. Database changes | • None |
| 12. Dataset requirements | None. |
| 13. Integration points | • Sits in front of every route registered from Phase 3 onward |
| 14. Testing requirements | • Rate-limit trigger test (Nth request rejected) • malformed-payload rejection test • missing-header/CORS rejection test |
| 15. Acceptance criteria | • Requests without valid input fail closed with a clear 4xx, never a 5xx crash |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/api-gateway. |
| 17. Dependencies | • Phase 1 |
| 18. Risks | • Overly strict rate limits break the dashboard's polling in Phase 11 — Mitigation: Tune limits per route class; revisit after Phase 11 load pattern is known |
| 19. Do NOT implement here | • DLP or risk logic • Audit log persistence (Phase 5) |

### Phase 2 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P02-013 | P2 | Cyber | Cyber 1 | express-rate-limit config per route class (auth vs general) | Phase 1 complete (auth middleware exists to sit behind the gateway) | Rate-limit middleware | Phase 1 | Rate-limit trigger test (Nth request rejected) | Requests without valid input fail closed with a clear 4xx, never a 5xx crash |
| T-P02-014 | P2 | Cyber | Cyber 4 | Helmet security headers + CORS allow-list finalized | Phase 1 complete (auth middleware exists to sit behind the gateway) | Rate-limit middleware | Phase 1 | Rate-limit trigger test (Nth request rejected) | Requests without valid input fail closed with a clear 4xx, never a 5xx crash |
| T-P02-015 | P2 | Cyber | Cyber 1 | Input-validation schema layer (Joi/Zod) on all mutating routes | Phase 1 complete (auth middleware exists to sit behind the gateway) | Rate-limit middleware | Phase 1 | Rate-limit trigger test (Nth request rejected) | Requests without valid input fail closed with a clear 4xx, never a 5xx crash |
| T-P02-016 | P2 | CS | CS 1 | Wire middleware order into the Express app entrypoint | Phase 1 complete (auth middleware exists to sit behind the gateway) | Rate-limit middleware | Phase 1 | Rate-limit trigger test (Nth request rejected) | Requests without valid input fail closed with a clear 4xx, never a 5xx crash |
| T-P02-017 | P2 | CS | CS 1 | Request-logging hook (pre-cursor to Phase 5 audit logging, not the audit log itself) | Phase 1 complete (auth middleware exists to sit behind the gateway) | Rate-limit middleware | Phase 1 | Rate-limit trigger test (Nth request rejected) | Requests without valid input fail closed with a clear 4xx, never a 5xx crash |

## PHASE 3 — DLP (Regex + Presidio + spaCy)

| 1. Objective | A DLP scanning service that detects PII, credentials, and structured secrets in text using Regex, Microsoft Presidio, and spaCy NER — matching notebook Cell 3's ReversibleDLPEngine.scan_and_redact, split from the redaction/restore half (Phase 4). |
| --- | --- |
| 2. Why this phase exists | DLP detection must exist and be independently testable before it is wired into reversible redaction (Phase 4) or the risk engine (Phase 6). |
| 3. Prerequisites | • Phase 2 complete (gateway exists to expose the internal DLP endpoint) |
| 7. Responsible person(s) | Cyber 2 (lead), AI 4 (Presidio/spaCy port + FastAPI wiring) |
| 8. Deliverables | • Standalone dlp-service (FastAPI) exposing /dlp/scan • Ported recognizer set • Measured recall/precision/FPR on ai4privacy sample |
| 9. Files / components | • ai-services/dlp-service/main.py • ai-services/dlp-service/recognizers.py • backend/src/services/dlpClient.js |
| 10. APIs required | • Internal: POST /dlp/scan {prompt} -> {entities[], token_map, sensitivityScore} (matches notebook Cell 13 contract) |
| 11. Database changes | • None yet — token persistence is Phase 4 |
| 12. Dataset requirements | ai4privacy/pii-masking-200k (public) for evaluation only. Do not train on it — Presidio/spaCy are pretrained. |
| 13. Integration points | • Called by backend via dlpClient.js • Feeds Phase 6 Risk Engine's dlp_detected_count input |
| 14. Testing requirements | • Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed • Regression test against notebook Cell 3's worked example (AWS key + email in a prompt) |
| 15. Acceptance criteria | • Detector flags a defined test set above a team-agreed recall threshold • Measured numbers logged to evaluationResults, not fabricated |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST (measured metrics) -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/dlp-engine. |
| 17. Dependencies | • Phase 2 |
| 18. Risks | • notebook demo prompt contains a fake but realistic-looking AWS key string — must never be reused verbatim in production test fixtures without clearly marking it synthetic — Mitigation: Regenerate a clearly-fake placeholder pattern for test fixtures; document in the migration matrix |
| 19. Do NOT implement here | • Reversible token restore/decrypt (Phase 4) • Risk scoring (Phase 6) |

### Phase 3 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P03-018 | P3 | Cyber | Cyber 2 | Define sensitive-data categories exactly as scoped in Chapter 1 (PII, credentials, structured secrets) — no invented categories | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |
| T-P03-019 | P3 | Cyber | Cyber 2 | Integrate DLP scan result into the (future) policy decision contract | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |
| T-P03-020 | P3 | AI | AI 4 | Port Presidio default recognizers + custom API-key PatternRecognizer from notebook Cell 3 | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |
| T-P03-021 | P3 | AI | AI 4 | Port spaCy en_core_web_lg NER pipeline (notebook Cell 0's ensure_spacy_model helper) | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |
| T-P03-022 | P3 | AI | AI 4 | Acquire ai4privacy/pii-masking-200k sample for evaluation (not training) | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |
| T-P03-023 | P3 | CS | CS 1 | Internal dlpClient.js to call the DLP microservice from the Node backend | Phase 2 complete (gateway exists to expose the internal DLP endpoint) | Standalone dlp-service (FastAPI) exposing /dlp/scan | Phase 2 | Labeled PII/credential test set -> recall/precision/false-positive rate actually measured, not assumed | Detector flags a defined test set above a team-agreed recall threshold |

## PHASE 4 — Reversible Encrypted Token Mapping (Redaction)

| 1. Objective | Full reversible-redaction lifecycle: encrypt detected entities into tokens, store a token map, and restore original values in the AI response — matching notebook Cell 3's restore_response and the Fernet-based token_map. |
| --- | --- |
| 2. Why this phase exists | DLP detection (Phase 3) alone is not useful without a safe way to let the redacted prompt go to the AI service and then un-redact the reply for the authorized employee. |
| 3. Prerequisites | • Phase 3 complete |
| 7. Responsible person(s) | Cyber 2 (lead) |
| 8. Deliverables | • Working redact -> AI call -> restore round trip • TTL-based automatic token expiry |
| 9. Files / components | • backend/src/models/TokenMapping.js • ai-services/dlp-service/redaction.py |
| 10. APIs required | • Internal: reuses /dlp/scan (returns token_map); new POST /dlp/restore {text, token_map} -> restored text |
| 11. Database changes | • tokenMappings collection: tokenId, encryptedValue, createdAt, TTL index (mandatory, not optional) |
| 12. Dataset requirements | None (reuses Phase 3's evaluation set for round-trip correctness tests). |
| 13. Integration points | • Sits between the DLP scan (Phase 3) and any outbound call to a generative-AI service |
| 14. Testing requirements | • Round-trip test: redact -> simulate AI reply referencing tokens -> restore -> original values recovered exactly • TTL expiry test: mapping unrecoverable after expiry window |
| 15. Acceptance criteria | • Round trip is lossless for every entity type in the Phase 3 test set • Encryption key is never found in application logs or committed artifacts |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/reversible-redaction. |
| 17. Dependencies | • Phase 3 |
| 18. Risks | • Encryption key handling done insecurely by a student team — Mitigation: Cyber 4 security-reviews the key-management code before merge, ahead of the formal Phase 13 test pass |
| 19. Do NOT implement here | • Long-term audit trail of redaction events (Phase 5) |

### Phase 4 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P04-024 | P4 | Cyber | Cyber 2 | Design AES-256/Fernet key management — key must live in a KMS/secret manager, never persisted alongside model artifacts (per notebook Cell 12's explicit warning) | Phase 3 complete | Working redact -> AI call -> restore round trip | Phase 3 | Round-trip test: redact -> simulate AI reply referencing tokens -> restore -> original values recovered exactly | Round trip is lossless for every entity type in the Phase 3 test set |
| T-P04-025 | P4 | Cyber | Cyber 2 | Enforce TTL-based automatic deletion of token mappings | Phase 3 complete | Working redact -> AI call -> restore round trip | Phase 3 | Round-trip test: redact -> simulate AI reply referencing tokens -> restore -> original values recovered exactly | Round trip is lossless for every entity type in the Phase 3 test set |
| T-P04-026 | P4 | AI | AI 4 | Port token generation + restore_response logic from notebook Cell 3 | Phase 3 complete | Working redact -> AI call -> restore round trip | Phase 3 | Round-trip test: redact -> simulate AI reply referencing tokens -> restore -> original values recovered exactly | Round trip is lossless for every entity type in the Phase 3 test set |
| T-P04-027 | P4 | CS | CS 1 | tokenMappings Mongoose schema with TTL index | Phase 3 complete | Working redact -> AI call -> restore round trip | Phase 3 | Round-trip test: redact -> simulate AI reply referencing tokens -> restore -> original values recovered exactly | Round trip is lossless for every entity type in the Phase 3 test set |

## PHASE 5 — Policy Engine + Audit Logging

| 1. Objective | A policy engine that turns a risk level into an enforcement action (Allow/Escalate/Block), plus an append-only audit log of every security decision. |
| --- | --- |
| 2. Why this phase exists | Risk scoring (Phase 6) is meaningless without a policy layer that acts on it, and every action must be auditable for the security-engineering framing of the project. |
| 3. Prerequisites | • Phase 4 complete |
| 7. Responsible person(s) | Cyber 3 (policy engine), Cyber 4 (audit logging) |
| 8. Deliverables | • Policy evaluation function (risk level -> action) • Working append-only audit log |
| 9. Files / components | • backend/src/services/policyEngine.js • backend/src/services/auditLogger.js • backend/src/models/Policy.js • backend/src/models/AuditLog.js |
| 10. APIs required | • Internal: evaluatePolicy(riskLevel) -> action • POST /internal/audit/log (called by every security decision point) |
| 11. Database changes | • policies collection • auditLogs collection (append-only, no delete route in app logic) |
| 12. Dataset requirements | None. |
| 13. Integration points | • Will receive input from Phase 6's Risk Engine once that phase lands; stub input accepted now for independent testing |
| 14. Testing requirements | • Policy decision test matrix (Low/Medium/High -> expected action) • Audit log write-then-attempt-delete test (must fail/be blocked) |
| 15. Acceptance criteria | • Every policy decision produces exactly one audit log entry • No code path can delete or mutate an existing audit log entry |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/policy-audit. |
| 17. Dependencies | • Phase 4 |
| 18. Risks | • Numeric risk-level thresholds are not yet finalized in academic documentation — Mitigation: Use placeholder thresholds now, re-confirm against Chapter 1 sign-off before Phase 6 is declared done (see Risk Register) |
| 19. Do NOT implement here | • Actual risk scoring math (Phase 6) |

### Phase 5 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P05-028 | P5 | Cyber | Cyber 3 | Define policy rule schema (ruleType, threshold, action) | Phase 4 complete | Policy evaluation function (risk level -> action) | Phase 4 | Policy decision test matrix (Low/Medium/High -> expected action) | Every policy decision produces exactly one audit log entry |
| T-P05-029 | P5 | Cyber | Cyber 4 | Append-only audit logging — no deletion path in application logic | Phase 4 complete | Policy evaluation function (risk level -> action) | Phase 4 | Policy decision test matrix (Low/Medium/High -> expected action) | Every policy decision produces exactly one audit log entry |
| T-P05-030 | P5 | Cyber | Cyber 4 | Audit log integrity checks (hash chaining or equivalent) | Phase 4 complete | Policy evaluation function (risk level -> action) | Phase 4 | Policy decision test matrix (Low/Medium/High -> expected action) | Every policy decision produces exactly one audit log entry |
| T-P05-031 | P5 | CS | CS 1 | policies and auditLogs Mongoose collections | Phase 4 complete | Policy evaluation function (risk level -> action) | Phase 4 | Policy decision test matrix (Low/Medium/High -> expected action) | Every policy decision produces exactly one audit log entry |
| T-P05-032 | P5 | CS | CS 2 | Admin UI stub for policy configuration | Phase 4 complete | Policy evaluation function (risk level -> action) | Phase 4 | Policy decision test matrix (Low/Medium/High -> expected action) | Every policy decision produces exactly one audit log entry |

## PHASE 6 — Phase 1 Rule-Based Risk Engine

| 1. Objective | Deterministic weighted-rule fusion of the voice-authenticity score, social-engineering score, and DLP sensitivity score into a single risk level, matching notebook Cell 4's UnifiedRiskEngine.calculate_phase1_risk. |
| --- | --- |
| 2. Why this phase exists | This is the mandatory baseline risk engine the whole demo depends on; Phase 2 (XGBoost/SHAP, Phase 13/22-equivalent) is conditional on top of it, never a replacement for it. |
| 3. Prerequisites | • Phase 5 complete (policy engine exists to consume the risk level) |
| 7. Responsible person(s) | Cyber 3 (lead) |
| 8. Deliverables | • Working Phase 1 risk-fusion function with documented, agreed weights • Combined-incident test scenarios passing |
| 9. Files / components | • backend/src/services/riskEngine.js |
| 10. APIs required | • Internal: POST /internal/risk/evaluate {deepfake_score, social_eng_score, dlp_detected_count} -> {risk_level, action, contributions} (matches notebook Cell 13 contract) |
| 11. Database changes | • incidents collection: riskLevel, sourceType, scores{}, status |
| 12. Dataset requirements | None (rule-based, no training data required). |
| 13. Integration points | • Consumes stubbed scores now; real scores arrive once Phases 7-9 land (Phase 10 wires them for real) |
| 14. Testing requirements | • Combined-incident test scenarios (Section 7.2-equivalent): benign, spoofed-voice, social-engineering, DLP-leak, combined |
| 15. Acceptance criteria | • All combined-incident scenarios produce the expected risk level and action • Functional validation, not a statistical accuracy metric, per Chapter 1 §6.4.5 |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/risk-engine-phase1. |
| 17. Dependencies | • Phase 5 |
| 18. Risks | • CONFLICT — the notebook hardcodes weights (deepfake 0.40 / social-engineering 0.35 / DLP 0.25) and a BLOCK threshold of 0.70, but Chapter 1 §6.4.5 explicitly states risk-level thresholds are 'to be defined during implementation.' The notebook's specific numbers were never approved in the academic documentation. — Mitigation: Do NOT silently adopt the notebook's numbers as final. Present them to the supervisor/team as a starting proposal (they are a reasonable prototype default) and get explicit sign-off before they become the documented baseline. |
| 19. Do NOT implement here | • Phase 2 XGBoost/SHAP model (conditional, later phase) • Any learned weighting — Phase 1 weights are configured, not trained |

### Phase 6 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P06-033 | P6 | Cyber | Cyber 3 | Implement weighted fusion logic | Phase 5 complete (policy engine exists to consume the risk level) | Working Phase 1 risk-fusion function with documented, agreed weights | Phase 5 | Combined-incident test scenarios (Section 7.2-equivalent): benign, spoofed-voice, social-engineering, DLP-leak, combined | All combined-incident scenarios produce the expected risk level and action |
| T-P06-034 | P6 | Cyber | Cyber 3 | Wire risk level into the Phase 5 policy engine | Phase 5 complete (policy engine exists to consume the risk level) | Working Phase 1 risk-fusion function with documented, agreed weights | Phase 5 | Combined-incident test scenarios (Section 7.2-equivalent): benign, spoofed-voice, social-engineering, DLP-leak, combined | All combined-incident scenarios produce the expected risk level and action |
| T-P06-035 | P6 | CS | CS 1 | Internal risk-evaluation endpoint plumbing | Phase 5 complete (policy engine exists to consume the risk level) | Working Phase 1 risk-fusion function with documented, agreed weights | Phase 5 | Combined-incident test scenarios (Section 7.2-equivalent): benign, spoofed-voice, social-engineering, DLP-leak, combined | All combined-incident scenarios produce the expected risk level and action |

## PHASE 7 — Faster-Whisper (Speech-to-Text)

| 1. Objective | A speech-to-text microservice using the pretrained Faster-Whisper model, matching notebook Cell 1's SpeechTranscriber, exposed for the mBERT social-engineering pipeline to consume. |
| --- | --- |
| 2. Why this phase exists | The mBERT classifier (Phase 9) operates on transcribed text, not raw audio — this phase must exist first. |
| 3. Prerequisites | • Phase 0 complete (can run in parallel with Phases 1-6 since it has no backend dependency) |
| 7. Responsible person(s) | AI 2 (lead) |
| 8. Deliverables | • Standalone whisper-service exposing a transcribe endpoint • CPU-fallback path validated (no GPU assumed) |
| 9. Files / components | • ai-services/whisper-service/main.py • ai-services/whisper-service/audio_processor.py |
| 10. APIs required | • Internal: POST /audio/transcribe {audio_path} -> {transcript} |
| 11. Database changes | • None |
| 12. Dataset requirements | Controlled/team-recorded audio samples for smoke testing. No public benchmark required for Whisper itself (pretrained, not fine-tuned). |
| 13. Integration points | • Consumed by Phase 9's mBERT classifier and Phase 10's AI Integration layer |
| 14. Testing requirements | • Transcription smoke test on 3-5 controlled audio clips • Latency measurement of the transcription step alone (feeds Phase 13's benchmark) |
| 15. Acceptance criteria | • Service returns a plausible transcript for each smoke-test clip • CPU fallback confirmed functional if no GPU is available |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/whisper-service. |
| 17. Dependencies | • Phase 0 |
| 18. Risks | • No GPU confirmed available for the team — Mitigation: CPU-fallback path is a hard acceptance-criterion, not optional, even if slower than the latency target |
| 19. Do NOT implement here | • Fine-tuning Whisper (pretrained-only per Chapter 1) • Arabic upgrade (optional, out of baseline) |

### Phase 7 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P07-036 | P7 | AI | AI 2 | Wrap notebook Cell 1's AudioProcessor.preprocess_audio (resampling, top_db trimming) as a reusable module | Phase 0 complete (can run in parallel with Phases 1-6 since it has no backend dependency) | Standalone whisper-service exposing a transcribe endpoint | Phase 0 | Transcription smoke test on 3-5 controlled audio clips | Service returns a plausible transcript for each smoke-test clip |
| T-P07-037 | P7 | AI | AI 2 | Wrap SpeechTranscriber (pretrained faster-whisper 'base' model) as a callable service | Phase 0 complete (can run in parallel with Phases 1-6 since it has no backend dependency) | Standalone whisper-service exposing a transcribe endpoint | Phase 0 | Transcription smoke test on 3-5 controlled audio clips | Service returns a plausible transcript for each smoke-test clip |
| T-P07-038 | P7 | AI | AI 2 | Validate on a small controlled-audio sample set | Phase 0 complete (can run in parallel with Phases 1-6 since it has no backend dependency) | Standalone whisper-service exposing a transcribe endpoint | Phase 0 | Transcription smoke test on 3-5 controlled audio clips | Service returns a plausible transcript for each smoke-test clip |

## PHASE 8 — RawNet2 (Voice Deepfake Detection)

| 1. Objective | A voice-authenticity classifier using the pretrained RawNet2 anti-spoofing model (SincConv + FMS + ResBlock + GRU architecture from notebook Cells 10-11), with a validated CPU fallback. |
| --- | --- |
| 2. Why this phase exists | This is one of the three mandatory Phase 1 risk-fusion inputs; it must be independently functional and independently tested before Phase 10 wires it in. |
| 3. Prerequisites | • Phase 0 complete (can run in parallel with Phases 1-7) |
| 7. Responsible person(s) | AI 1 (lead) |
| 8. Deliverables | • Standalone voice-deepfake-service • Real ASVspoof-based evaluation (EER, ROC-AUC) replacing the notebook's simulated scores |
| 9. Files / components | • ai-services/voice-deepfake-service/main.py • ai-services/voice-deepfake-service/rawnet2.py |
| 10. APIs required | • Internal: POST /audio/analyze-deepfake {audio_path} -> {authenticity_score, is_spoofed} |
| 11. Database changes | • None (evaluation results go to evaluationResults in Phase 13/19) |
| 12. Dataset requirements | ASVspoof 2019/2021 (real/public) for evaluation. WaveFake (real/public) as a secondary evaluation source. No team-generated synthetic data for this component. |
| 13. Integration points | • Consumed by Phase 10's AI Integration layer and Phase 6's risk fusion |
| 14. Testing requirements | • Real ASVspoof protocol evaluation producing an actual EER/ROC-AUC, replacing notebook Cell 14's simulated bonafide/spoofed score distributions • CPU-fallback latency test |
| 15. Acceptance criteria | • A real (not simulated) EER is measured and logged to evaluationResults • Service fails loudly (not silently with random scores) if weights are missing |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST (real EER) -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/rawnet2-service. |
| 17. Dependencies | • Phase 0 |
| 18. Risks | • FLAGGED — notebook Cell 14's EER/ROC-AUC numbers are computed from np.random.normal-generated bonafide/spoofed score distributions (SIMULATED SCORES), not a real model run. These numbers must never be quoted in the defense as measured accuracy. — Mitigation: This phase's acceptance criterion explicitly requires a real ASVspoof run before any number is reported • No confirmed GPU — Mitigation: Same CPU-fallback mitigation as Phase 7 |
| 19. Do NOT implement here | • Voiceprint/speaker verification (Future Work) • Fine-tuning beyond the optional path |

### Phase 8 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P08-039 | P8 | AI | AI 1 | Port the RawNet2 architecture (SincConv, FMS, ResBlock, RawNet2 classes) from notebook Cells 10-11 unchanged | Phase 0 complete (can run in parallel with Phases 1-7) | Standalone voice-deepfake-service | Phase 0 | Real ASVspoof protocol evaluation producing an actual EER/ROC-AUC, replacing notebook Cell 14's simulated bonafide/spoofed score distributions | A real (not simulated) EER is measured and logged to evaluationResults |
| T-P08-040 | P8 | AI | AI 1 | Source a real ASVspoof-trained checkpoint for RAWNET2_WEIGHTS_PATH — baseline is the pretrained checkpoint; fine-tuning is optional per project rules | Phase 0 complete (can run in parallel with Phases 1-7) | Standalone voice-deepfake-service | Phase 0 | Real ASVspoof protocol evaluation producing an actual EER/ROC-AUC, replacing notebook Cell 14's simulated bonafide/spoofed score distributions | A real (not simulated) EER is measured and logged to evaluationResults |
| T-P08-041 | P8 | AI | AI 1 | Remove/replace the notebook's DummyVoiceDetector fallback with a clear startup failure if no real weights are found (a silent random-score fallback must never reach production) | Phase 0 complete (can run in parallel with Phases 1-7) | Standalone voice-deepfake-service | Phase 0 | Real ASVspoof protocol evaluation producing an actual EER/ROC-AUC, replacing notebook Cell 14's simulated bonafide/spoofed score distributions | A real (not simulated) EER is measured and logged to evaluationResults |

## PHASE 9 — mBERT + Classification Head (Social Engineering)

| 1. Objective | A multi-label social-engineering classifier: pretrained mBERT encoder (bert-base-multilingual-cased) plus a project-specific classification head trained on labeled data, per notebook Cells 2, 6-8. |
| --- | --- |
| 2. Why this phase exists | mBERT is an encoder, not a ready-made classifier — the project-specific head must be trained before this component can produce the social-engineering score Phase 6 needs. |
| 3. Prerequisites | • Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) |
| 7. Responsible person(s) | AI 3 (lead) |
| 8. Deliverables | • Trained classification head + saved state dict + tokenizer • Measured per-label precision/recall/F1 |
| 9. Files / components | • ai-services/social-engineering-service/model.py • ai-services/social-engineering-service/train.py • easp_ai_artifacts/mbert_social_engineering.pt • easp_ai_artifacts/mbert_tokenizer/ |
| 10. APIs required | • Internal: POST /nlp/classify {transcript} -> {urgency, authority_impersonation, credential_request, payment_request, scores} |
| 11. Database changes | • None directly (evaluation results go to evaluationResults) |
| 12. Dataset requirements | SMS Spam Collection (real/public) with regex-derived proxy multi-labels (urgency, authority_impersonation, credential_request, payment_request), per notebook Cell 6. Enron Email and public phishing corpora as documented alternate/supplementary sources. CoNLL-2003 not directly used by this component (NER, used by Phase 3's spaCy pipeline instead). |
| 13. Integration points | • Consumes transcripts from Phase 7's Whisper service for live-audio use • Feeds Phase 6's risk fusion |
| 14. Testing requirements | • Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) • Label-imbalance check (report actual distribution, not assumed balance) |
| 15. Acceptance criteria | • Per-label F1 is measured and logged, not asserted • Domain-gap limitation is documented alongside the numbers, not hidden |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/mbert-social-engineering. |
| 17. Dependencies | • Phase 7 (for live-audio path) |
| 18. Risks | • Domain gap: trained on SMS spam text, evaluated conceptually against voice-call social-engineering scenarios — Mitigation: Explicitly documented as a known limitation, not silently corrected; flagged again at Phase 19-equivalent evaluation • Regex-derived labels are a proxy, not ground truth — Mitigation: Treat early F1 numbers as directional; do not present as validated accuracy without caveat |
| 19. Do NOT implement here | • Full fine-tuning of the mBERT encoder itself (only the head is trained, per Chapter 1's encoder-not-classifier framing) • Arabic upgrade to XLM-R (optional, out of baseline) |

### Phase 9 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P09-042 | P9 | AI | AI 3 | Port SocialEngineeringmBERT model + SocialEngineeringDetector from notebook Cell 2 | Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) | Trained classification head + saved state dict + tokenizer | Phase 7 (for live-audio path) | Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) | Per-label F1 is measured and logged, not asserted |
| T-P09-043 | P9 | AI | AI 3 | Port the SMS Spam Collection loading + regex-based multi-label mapping from notebook Cell 6 | Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) | Trained classification head + saved state dict + tokenizer | Phase 7 (for live-audio path) | Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) | Per-label F1 is measured and logged, not asserted |
| T-P09-044 | P9 | AI | AI 3 | Port the class-weighted (pos_weight) training loop from notebook Cell 7 | Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) | Trained classification head + saved state dict + tokenizer | Phase 7 (for live-audio path) | Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) | Per-label F1 is measured and logged, not asserted |
| T-P09-045 | P9 | AI | AI 3 | Port per-label precision/recall/F1 evaluation from notebook Cell 8 | Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) | Trained classification head + saved state dict + tokenizer | Phase 7 (for live-audio path) | Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) | Per-label F1 is measured and logged, not asserted |
| T-P09-046 | P9 | AI | AI 3 | Document the domain gap: labels are proxy-derived from SMS spam text via regex, not hand-annotated call transcripts (already a stated limitation in Chapter 1 §6.5) — do not overstate accuracy | Phase 7 complete (needs transcribed text as training/eval input for real call-audio use, though initial training can proceed on text directly) | Trained classification head + saved state dict + tokenizer | Phase 7 (for live-audio path) | Held-out test split evaluation (precision/recall/F1 per label, per notebook Cell 8) | Per-label F1 is measured and logged, not asserted |

## PHASE 10 — AI Integration (FastAPI Microservice)

| 1. Objective | A single FastAPI microservice wrapping DLP, voice-deepfake, transcription, and social-engineering components behind three production endpoints, matching notebook Cell 13's EASP_AIService/app structure, consumed by the Node.js backend's Security Engine layer. |
| --- | --- |
| 2. Why this phase exists | Phases 3-4 and 7-9 are independently-built components; this phase is the seam that makes them one callable service for the backend. |
| 3. Prerequisites | • Phases 3, 4, 6, 7, 8, 9 all independently functional and tested — do not integrate until each model works independently |
| 7. Responsible person(s) | AI 4 (lead), CS 1 (backend-side integration) |
| 8. Deliverables | • Running FastAPI microservice reachable from the Node backend • End-to-end call: prompt/audio in -> DLP + voice + social-engineering + risk out |
| 9. Files / components | • ai-services/ai-gateway/main.py (or equivalent consolidated entrypoint) • backend/src/services/aiServiceClient.js |
| 10. APIs required | • POST /dlp/scan • POST /audio/analyze • POST /risk/evaluate (all three from notebook Cell 13, now genuinely served, not just defined) |
| 11. Database changes | • None new — writes flow through to incidents/evaluationResults defined in earlier phases |
| 12. Dataset requirements | None new — this phase is integration, not modeling. |
| 13. Integration points | • This IS the integration point between the AI services (Phases 3-9) and the Node backend (Phases 1-6) |
| 14. Testing requirements | • Live HTTP call to all three endpoints (not just unit-level function calls) • Failure-mode test: one sub-model down -> service returns a clear error, not a silent wrong answer |
| 15. Acceptance criteria | • All three endpoints are reachable over HTTP from the Node backend in the Docker network • A full request (audio + prompt) produces a coherent combined response |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST (live HTTP) -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/ai-integration. |
| 17. Dependencies | • Phases 3, 4, 6, 7, 8, 9 |
| 18. Risks | • Internal AI services exposed beyond the internal Docker network — Mitigation: Cyber 4 verifies network isolation before this phase is marked done |
| 19. Do NOT implement here | • Phase 2 XGBoost/SHAP wiring (kept separate, conditional — see Phase 13's evaluation gate) |

### Phase 10 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P10-047 | P10 | Cyber | Cyber 4 | Security-review the internal REST contract (auth between Node backend and Python services, internal-network-only exposure) | Phases 3, 4, 6, 7, 8, 9 all independently functional and tested — do not integrate until each model works independently | Running FastAPI microservice reachable from the Node backend | Phases 3, 4, 6, 7, 8, 9 | Live HTTP call to all three endpoints (not just unit-level function calls) | All three endpoints are reachable over HTTP from the Node backend in the Docker network |
| T-P10-048 | P10 | AI | AI 4 | Assemble EASP_AIService wrapper class from notebook Cell 13 | Phases 3, 4, 6, 7, 8, 9 all independently functional and tested — do not integrate until each model works independently | Running FastAPI microservice reachable from the Node backend | Phases 3, 4, 6, 7, 8, 9 | Live HTTP call to all three endpoints (not just unit-level function calls) | All three endpoints are reachable over HTTP from the Node backend in the Docker network |
| T-P10-049 | P10 | AI | AI 4 | Stand up the real FastAPI app with /dlp/scan, /audio/analyze, /risk/evaluate — the notebook's own comment notes the original version was 'just a class, no app, no endpoints' and had to be fixed; verify the production port is genuinely reachable over HTTP, not just importable | Phases 3, 4, 6, 7, 8, 9 all independently functional and tested — do not integrate until each model works independently | Running FastAPI microservice reachable from the Node backend | Phases 3, 4, 6, 7, 8, 9 | Live HTTP call to all three endpoints (not just unit-level function calls) | All three endpoints are reachable over HTTP from the Node backend in the Docker network |
| T-P10-050 | P10 | CS | CS 1 | Node backend Security Engine layer calling the FastAPI service over the internal Docker network | Phases 3, 4, 6, 7, 8, 9 all independently functional and tested — do not integrate until each model works independently | Running FastAPI microservice reachable from the Node backend | Phases 3, 4, 6, 7, 8, 9 | Live HTTP call to all three endpoints (not just unit-level function calls) | All three endpoints are reachable over HTTP from the Node backend in the Docker network |

## PHASE 11 — Security Dashboard

| 1. Objective | A role-aware React dashboard distinguishing Detected Event / Risk Level / Policy Action / Model Result / Measured Performance, with a hard rule that any metric without a real measured value renders as 'No measured data available' rather than a placeholder number. |
| --- | --- |
| 2. Why this phase exists | This is the human-facing surface analysts and the supervisor will actually look at during the defense; it must never display fabricated numbers. |
| 3. Prerequisites | • Phase 5 (policy/audit data to display) and Phase 10 (AI results to display) — UI scaffolding may start earlier in parallel using mocked responses |
| 7. Responsible person(s) | CS 2 (lead) |
| 8. Deliverables | • Working dashboard with the three role views • Verified fallback behavior for unmeasured metrics |
| 9. Files / components | • frontend/src/pages/Dashboard.jsx • frontend/src/components/IncidentTable.jsx • frontend/src/components/MetricsPanel.jsx |
| 10. APIs required | • GET /api/v1/incidents • GET /api/v1/audit-logs (role-restricted) • GET /api/v1/metrics |
| 11. Database changes | • Reads only — no new collections |
| 12. Dataset requirements | None. |
| 13. Integration points | • Consumes Phase 5's audit log and Phase 6's risk-level output |
| 14. Testing requirements | • Role-based visibility test (Employee cannot see Administrator-only audit detail) • Unmeasured-metric fallback test (component renders the literal fallback string, never a fabricated number) |
| 15. Acceptance criteria | • Each role sees the correct subset of data • No placeholder numbers ever render for an unmeasured metric |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/security-dashboard. |
| 17. Dependencies | • Phase 5 • Phase 10 (for live data; can demo with mocks earlier) |
| 18. Risks | • Team tempted to hardcode a demo number for a metric not yet measured — Mitigation: Explicit acceptance criterion above blocks this; Cyber 4 spot-checks before merge |
| 19. Do NOT implement here | • SIEM export (should-implement, later/optional) |

### Phase 11 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P11-051 | P11 | Cyber | Cyber 4 | Review that the dashboard does not leak sensitive redacted values to unauthorized roles | Phase 5 (policy/audit data to display) and Phase 10 (AI results to display) — UI scaffolding may start earlier in parallel using mocked responses | Working dashboard with the three role views | Phase 5, Phase 10 (for live data; can demo with mocks earlier) | Role-based visibility test (Employee cannot see Administrator-only audit detail) | Each role sees the correct subset of data |
| T-P11-052 | P11 | CS | CS 2 | Role-aware routing (Employee vs Analyst vs Administrator views) | Phase 5 (policy/audit data to display) and Phase 10 (AI results to display) — UI scaffolding may start earlier in parallel using mocked responses | Working dashboard with the three role views | Phase 5, Phase 10 (for live data; can demo with mocks earlier) | Role-based visibility test (Employee cannot see Administrator-only audit detail) | Each role sees the correct subset of data |
| T-P11-053 | P11 | CS | CS 2 | Dashboard components consuming audit log / incident / evaluationResults data | Phase 5 (policy/audit data to display) and Phase 10 (AI results to display) — UI scaffolding may start earlier in parallel using mocked responses | Working dashboard with the three role views | Phase 5, Phase 10 (for live data; can demo with mocks earlier) | Role-based visibility test (Employee cannot see Administrator-only audit detail) | Each role sees the correct subset of data |
| T-P11-054 | P11 | CS | CS 2 | Enforce the 'No measured data available' fallback at the component level | Phase 5 (policy/audit data to display) and Phase 10 (AI results to display) — UI scaffolding may start earlier in parallel using mocked responses | Working dashboard with the three role views | Phase 5, Phase 10 (for live data; can demo with mocks earlier) | Role-based visibility test (Employee cannot see Administrator-only audit detail) | Each role sees the correct subset of data |

## PHASE 12 — End-to-End Integration

| 1. Objective | Wire every prior phase into one live pipeline: prompt/voice in -> DLP/AI analysis -> risk fusion -> policy decision -> audit log -> dashboard update, replacing all mocked responses with real service calls. |
| --- | --- |
| 2. Why this phase exists | This is the first point at which the system is demonstrable as a whole rather than as independently-tested parts. |
| 3. Prerequisites | • Phases 1-11 complete |
| 7. Responsible person(s) | CS 1 (lead), all teams (integration milestone) |
| 8. Deliverables | • Full pipeline runnable end to end on a controlled demo scenario |
| 9. Files / components | • backend/src/routes/index.js (final route wiring) |
| 10. APIs required | • All previously defined endpoints, now called for real in sequence |
| 11. Database changes | • No schema changes — this phase is wiring, not new storage |
| 12. Dataset requirements | None new. |
| 13. Integration points | • Every phase's integration point becomes live here |
| 14. Testing requirements | • Re-run the notebook's own combined-incident scenarios (Cell 5's End-to-End Simulation Pipeline) now with real model outputs instead of mocks |
| 15. Acceptance criteria | • The same scenarios that passed with mocked data in earlier phases now pass with live data |
| 16. Definition of Done | IMPLEMENT -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to develop (integration checkpoint). |
| 17. Dependencies | • Phases 1-11 |
| 18. Risks | • Integration risk concentrated here — most likely point for cross-team breakage — Mitigation: Freeze feature work for 2-3 days around this phase; all hands on integration bugs |
| 19. Do NOT implement here | • Any new feature — this phase wires existing features together only |

### Phase 12 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P12-055 | P12 | Cyber | Cyber 4 | Verify RBAC/audit logging holds end to end, not just per-component | Phases 1-11 complete | Full pipeline runnable end to end on a controlled demo scenario | Phases 1-11 | Re-run the notebook's own combined-incident scenarios (Cell 5's End-to-End Simulation Pipeline) now with real model outputs instead of mocks | The same scenarios that passed with mocked data in earlier phases now pass with live data |
| T-P12-056 | P12 | AI | AI 4 | Confirm AI Integration (Phase 10) responses flow unmocked into the risk engine | Phases 1-11 complete | Full pipeline runnable end to end on a controlled demo scenario | Phases 1-11 | Re-run the notebook's own combined-incident scenarios (Cell 5's End-to-End Simulation Pipeline) now with real model outputs instead of mocks | The same scenarios that passed with mocked data in earlier phases now pass with live data |
| T-P12-057 | P12 | CS | CS 1 | Replace every mocked frontend/backend call with the real service call | Phases 1-11 complete | Full pipeline runnable end to end on a controlled demo scenario | Phases 1-11 | Re-run the notebook's own combined-incident scenarios (Cell 5's End-to-End Simulation Pipeline) now with real model outputs instead of mocks | The same scenarios that passed with mocked data in earlier phases now pass with live data |
| T-P12-058 | P12 | CS | CS 1 | End-to-end wiring across Express routes | Phases 1-11 complete | Full pipeline runnable end to end on a controlled demo scenario | Phases 1-11 | Re-run the notebook's own combined-incident scenarios (Cell 5's End-to-End Simulation Pipeline) now with real model outputs instead of mocks | The same scenarios that passed with mocked data in earlier phases now pass with live data |

## PHASE 13 — Security + AI + Performance Testing

| 1. Objective | Formal test pass: cybersecurity test cases, AI/data-science evaluation (final EER, F1, DLP recall/precision/FPR), and end-to-end latency measurement against the <=3s target. |
| --- | --- |
| 2. Why this phase exists | Supersedes ad hoc spot-checks from Phases 3-9 with final, dated, reproducible numbers usable in the defense — and this is where the XGBoost/SHAP go/no-go decision (conditional Phase 2 risk engine) is made from real data. |
| 3. Prerequisites | • Phase 12 complete |
| 7. Responsible person(s) | Cyber 4 (security tests), AI 4 / Data Science leads (AI evaluation), CS 1 (performance) |
| 8. Deliverables | • Signed-off security test report • Final measured AI metrics logged to evaluationResults • Latency report • Phase 2 go/no-go decision, documented either way |
| 9. Files / components | • tests/security/ • tests/ai-evaluation/ • docs/evaluation-results.md |
| 10. APIs required | • No new endpoints — exercises existing ones |
| 11. Database changes | • evaluationResults collection populated with final, dated, versioned numbers |
| 12. Dataset requirements | Real ASVspoof split for RawNet2, held-out SMS Spam split for mBERT, ai4privacy sample for DLP. If pursuing Phase 2: real analyst-labeled incident data only — notebook Cell 9's synthetic fallback (np.random-generated features/labels) must not be used for a number quoted in the defense. |
| 13. Integration points | • Exercises the full Phase 12 pipeline under test conditions |
| 14. Testing requirements | • Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' • Every AI component has one final, dated, reproducible measured result |
| 15. Acceptance criteria | • A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way • No number in the evaluation report is untraceable to an actual run |
| 16. Definition of Done | IMPLEMENT (test harness) -> RUN -> TEST -> FIX -> VERIFY -> DOCUMENT -> COMMIT to feature/formal-testing. |
| 17. Dependencies | • Phase 12 |
| 18. Risks | • Temptation to reuse notebook Cell 9's synthetic XGBoost data or Cell 14's simulated RawNet2 scores as 'final' numbers — Mitigation: Explicitly forbidden by this phase's acceptance criteria; migration matrix (below) flags both as non-production • Team-generated synthetic social-engineering/incident labels may be too small a corpus for meaningful evaluation — Mitigation: Report actual corpus size at the end of labeling, not assumed in advance |
| 19. Do NOT implement here | • Phase 2 XGBoost+SHAP implementation itself — this phase only makes the go/no-go call; implementation (if approved) is a separate follow-on task, not part of the 15-phase baseline |

### Phase 13 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P13-059 | P13 | Cyber | Cyber 4 | Security test cases: unauthorized access, privilege escalation, invalid/expired JWT, brute-force/rate-limit behavior, sensitive-data leakage, prompt-injection cases (OWASP-LLM01-aligned), malformed API requests, session/token abuse — each with documented input, expected output, actual result | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-060 | P13 | AI | AI 1 | Final EER for RawNet2 on real ASVspoof data (not the notebook's simulated distributions) | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-061 | P13 | AI | AI 3 | Final per-label precision/recall/F1 for mBERT+head | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-062 | P13 | AI | AI 4 | Final DLP recall/precision/FPR | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-063 | P13 | AI | AI 4 | Go/no-go call on Phase 2 XGBoost+SHAP: only proceed if real analyst-labeled incident data (not notebook Cell 9's synthetic X_sim/y_sim) is actually sufficient — report the real corpus size before deciding, don't assume it in advance | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-064 | P13 | AI | CS 1 | Wall-clock latency measurement per pipeline stage and end-to-end, per notebook Cell 11's benchmarking structure | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |
| T-P13-065 | P13 | CS | CS 1 | Load-test harness for the latency measurement | Phase 12 complete | Signed-off security test report | Phase 12 | Every security test case above has a real pass/fail result recorded — none marked 'assumed passing' | A real measured latency number exists, whether or not it meets the <=3s target — reported honestly either way |

## PHASE 14 — Final Validation + Demo

| 1. Objective | Defense-ready state: rehearsed demo script, all documentation synchronized with what was actually built, final measured-metrics summary. |
| --- | --- |
| 2. Why this phase exists | This is the deliverable the supervisor/committee evaluates — everything before this phase was building toward this state. |
| 3. Prerequisites | • Phase 13 complete |
| 7. Responsible person(s) | All teams |
| 8. Deliverables | • Updated docs/ reflecting real implementation (not the aspirational Chapter 1 baseline where they diverge) • Final measured-metrics summary • Rehearsed demo script |
| 9. Files / components | • docs/final-report/ • docs/demo-script.md |
| 10. APIs required | • None new |
| 11. Database changes | • None new |
| 12. Dataset requirements | None new — this phase consolidates, does not generate. |
| 13. Integration points | • Full-system rehearsal of the Phase 12 pipeline |
| 14. Testing requirements | • Full rehearsal run-through of all demo scenarios at least twice |
| 15. Acceptance criteria | • Every claim in the documentation is traceable to either (a) working code or (b) an explicitly labeled Future Work item — no gap between what's written and what's built |
| 16. Definition of Done | IMPLEMENT (docs/script) -> RUN (rehearsal) -> TEST -> FIX -> VERIFY (supervisor pre-review if possible) -> DOCUMENT -> COMMIT to main (release tag). |
| 17. Dependencies | • Phase 13 |
| 18. Risks | • Documentation drift — Chapter 1's aspirational claims not updated to match what was actually built — Mitigation: Explicit acceptance criterion above; assign one person (AI 4 or CS 1) as documentation-accuracy owner for this phase |
| 19. Do NOT implement here | • Any Future Work item (image/video deepfake, production PBX, universal HTTPS interception, threat intelligence, voiceprint verification, federated learning, autoencoder anomaly detection) — none of these appear in this phase or any phase above |

### Phase 14 — Task Table (Cyber / AI / CS tasks, fields 4-6)

| Task ID | Ph. | Team | Person | Task | Input | Output | Dep. | Test | Acceptance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-P14-066 | P14 | Cyber | Cyber 4 | Final review that no security claim in the documentation exceeds what Phase 13 actually verified | Phase 13 complete | Updated docs/ reflecting real implementation (not the aspirational Chapter 1 baseline where they diverge) | Phase 13 | Full rehearsal run-through of all demo scenarios at least twice | Every claim in the documentation is traceable to either (a) working code or (b) an explicitly labeled Future Work item — no gap between what's written and what's built |
| T-P14-067 | P14 | AI | AI 4 | Final measured-metrics summary compiled from evaluationResults | Phase 13 complete | Updated docs/ reflecting real implementation (not the aspirational Chapter 1 baseline where they diverge) | Phase 13 | Full rehearsal run-through of all demo scenarios at least twice | Every claim in the documentation is traceable to either (a) working code or (b) an explicitly labeled Future Work item — no gap between what's written and what's built |
| T-P14-068 | P14 | CS | CS 1 | Rehearsed demo script covering the benign / spoofed-voice / social-engineering / DLP-leak / combined-incident scenarios | Phase 13 complete | Updated docs/ reflecting real implementation (not the aspirational Chapter 1 baseline where they diverge) | Phase 13 | Full rehearsal run-through of all demo scenarios at least twice | Every claim in the documentation is traceable to either (a) working code or (b) an explicitly labeled Future Work item — no gap between what's written and what's built |

# 7. Master Phase Roadmap

| Phase | Title | Lead(s) | Depends On | Complexity |
| --- | --- | --- | --- | --- |
| P0 | Foundation | CS 1 | None | Low-Medium |
| P1 | Authentication + JWT + RBAC | Cyber 1 | Phase 0 | Low-Medium |
| P2 | API Gateway + Security Middleware | Cyber 1 | Phase 1 | Low-Medium |
| P3 | DLP (Regex + Presidio + spaCy) | Cyber 2 | Phase 2 | Medium |
| P4 | Reversible Encrypted Token Mapping (Redaction) | Cyber 2 | Phase 3 | Medium |
| P5 | Policy Engine + Audit Logging | Cyber 3 | Phase 4 | Medium |
| P6 | Phase 1 Rule-Based Risk Engine | Cyber 3 | Phase 5 | Medium |
| P7 | Faster-Whisper (Speech-to-Text) | AI 2 | Phase 0 | Medium |
| P8 | RawNet2 (Voice Deepfake Detection) | AI 1 | Phase 0 | Medium |
| P9 | mBERT + Classification Head (Social Engineering) | AI 3 | Phase 7 (for live-audio path) | Medium |
| P10 | AI Integration (FastAPI Microservice) | AI 4 | Phases 3, 4, 6, 7, 8, 9 | Medium |
| P11 | Security Dashboard | CS 2 | Phase 5, Phase 10 (for live data; can demo with mocks earlier) | Medium |
| P12 | End-to-End Integration | CS 1 | Phases 1-11 | High |
| P13 | Security + AI + Performance Testing | Cyber 4 | Phase 12 | High |
| P14 | Final Validation + Demo | All teams | Phase 13 | Medium |

# 8. Team Responsibility Matrix

| Person | Phases Led / Contributed |
| --- | --- |
| Cyber 1 | P0 (secrets note), P1 (lead), P2 (lead) |
| Cyber 2 | P3 (lead), P4 (lead) |
| Cyber 3 | P5 (policy), P6 (lead) |
| Cyber 4 | P0, P2, P5 (audit), P8 (risk flag review), P10, P11, P13 (lead), P14 |
| AI 1 | P8 (lead), P10, P13 |
| AI 2 | P7 (lead), P10 |
| AI 3 | P9 (lead), P13 |
| AI 4 | P0, P3, P4, P10 (lead), P11, P13, P14 |
| CS 1 | P0, P1, P2, P3, P4, P5, P6, P10, P11, P12 (lead), P13, P14 |
| CS 2 | P0, P1, P5, P11 (lead), P14 |

# 9. Person-by-Person Task List

### Cyber 1

| Phase | Phase Title | Task |
| --- | --- | --- |
| P1 | Authentication + JWT + RBAC | Design JWT claims (userId, role, exp) and short-TTL/refresh strategy |
| P1 | Authentication + JWT + RBAC | Implement bcrypt hashing (>=12 salt rounds), never log plaintext passwords |
| P1 | Authentication + JWT + RBAC | Implement RBAC middleware enforcing Employee/Analyst/Administrator |
| P2 | API Gateway + Security Middleware | express-rate-limit config per route class (auth vs general) |
| P2 | API Gateway + Security Middleware | Input-validation schema layer (Joi/Zod) on all mutating routes |

### Cyber 2

| Phase | Phase Title | Task |
| --- | --- | --- |
| P3 | DLP (Regex + Presidio + spaCy) | Define sensitive-data categories exactly as scoped in Chapter 1 (PII, credentials, structured secrets) — no invented categories |
| P3 | DLP (Regex + Presidio + spaCy) | Integrate DLP scan result into the (future) policy decision contract |
| P4 | Reversible Encrypted Token Mapping (Redaction) | Design AES-256/Fernet key management — key must live in a KMS/secret manager, never persisted alongside model artifacts (per notebook Cell 12's explicit warning) |
| P4 | Reversible Encrypted Token Mapping (Redaction) | Enforce TTL-based automatic deletion of token mappings |

### Cyber 3

| Phase | Phase Title | Task |
| --- | --- | --- |
| P5 | Policy Engine + Audit Logging | Define policy rule schema (ruleType, threshold, action) |
| P6 | Phase 1 Rule-Based Risk Engine | Implement weighted fusion logic |
| P6 | Phase 1 Rule-Based Risk Engine | Wire risk level into the Phase 5 policy engine |

### Cyber 4

| Phase | Phase Title | Task |
| --- | --- | --- |
| P0 | Foundation | Set up .env.example with no real secrets + secret-scanning note in README |
| P2 | API Gateway + Security Middleware | Helmet security headers + CORS allow-list finalized |
| P5 | Policy Engine + Audit Logging | Append-only audit logging — no deletion path in application logic |
| P5 | Policy Engine + Audit Logging | Audit log integrity checks (hash chaining or equivalent) |
| P10 | AI Integration (FastAPI Microservice) | Security-review the internal REST contract (auth between Node backend and Python services, internal-network-only exposure) |
| P11 | Security Dashboard | Review that the dashboard does not leak sensitive redacted values to unauthorized roles |
| P12 | End-to-End Integration | Verify RBAC/audit logging holds end to end, not just per-component |
| P13 | Security + AI + Performance Testing | Security test cases: unauthorized access, privilege escalation, invalid/expired JWT, brute-force/rate-limit behavior, sensitive-data leakage, prompt-injection cases (OWASP-LLM01-aligned), malformed API requests, session/token abuse — each with documented input, expected output, actual result |
| P14 | Final Validation + Demo | Final review that no security claim in the documentation exceeds what Phase 13 actually verified |

### AI 1

| Phase | Phase Title | Task |
| --- | --- | --- |
| P8 | RawNet2 (Voice Deepfake Detection) | Port the RawNet2 architecture (SincConv, FMS, ResBlock, RawNet2 classes) from notebook Cells 10-11 unchanged |
| P8 | RawNet2 (Voice Deepfake Detection) | Source a real ASVspoof-trained checkpoint for RAWNET2_WEIGHTS_PATH — baseline is the pretrained checkpoint; fine-tuning is optional per project rules |
| P8 | RawNet2 (Voice Deepfake Detection) | Remove/replace the notebook's DummyVoiceDetector fallback with a clear startup failure if no real weights are found (a silent random-score fallback must never reach production) |
| P13 | Security + AI + Performance Testing | Final EER for RawNet2 on real ASVspoof data (not the notebook's simulated distributions) |

### AI 2

| Phase | Phase Title | Task |
| --- | --- | --- |
| P7 | Faster-Whisper (Speech-to-Text) | Wrap notebook Cell 1's AudioProcessor.preprocess_audio (resampling, top_db trimming) as a reusable module |
| P7 | Faster-Whisper (Speech-to-Text) | Wrap SpeechTranscriber (pretrained faster-whisper 'base' model) as a callable service |
| P7 | Faster-Whisper (Speech-to-Text) | Validate on a small controlled-audio sample set |

### AI 3

| Phase | Phase Title | Task |
| --- | --- | --- |
| P9 | mBERT + Classification Head (Social Engineering) | Port SocialEngineeringmBERT model + SocialEngineeringDetector from notebook Cell 2 |
| P9 | mBERT + Classification Head (Social Engineering) | Port the SMS Spam Collection loading + regex-based multi-label mapping from notebook Cell 6 |
| P9 | mBERT + Classification Head (Social Engineering) | Port the class-weighted (pos_weight) training loop from notebook Cell 7 |
| P9 | mBERT + Classification Head (Social Engineering) | Port per-label precision/recall/F1 evaluation from notebook Cell 8 |
| P9 | mBERT + Classification Head (Social Engineering) | Document the domain gap: labels are proxy-derived from SMS spam text via regex, not hand-annotated call transcripts (already a stated limitation in Chapter 1 §6.5) — do not overstate accuracy |
| P13 | Security + AI + Performance Testing | Final per-label precision/recall/F1 for mBERT+head |

### AI 4

| Phase | Phase Title | Task |
| --- | --- | --- |
| P0 | Foundation | Create data/raw, data/processed, data/evaluation folders + DATASETS.md tracking sheet |
| P0 | Foundation | Begin licensing verification for ASVspoof 2019/2021, WaveFake, SMS Spam Collection, Enron Email, ai4privacy/pii-masking-200k, CoNLL-2003 |
| P3 | DLP (Regex + Presidio + spaCy) | Port Presidio default recognizers + custom API-key PatternRecognizer from notebook Cell 3 |
| P3 | DLP (Regex + Presidio + spaCy) | Port spaCy en_core_web_lg NER pipeline (notebook Cell 0's ensure_spacy_model helper) |
| P3 | DLP (Regex + Presidio + spaCy) | Acquire ai4privacy/pii-masking-200k sample for evaluation (not training) |
| P4 | Reversible Encrypted Token Mapping (Redaction) | Port token generation + restore_response logic from notebook Cell 3 |
| P10 | AI Integration (FastAPI Microservice) | Assemble EASP_AIService wrapper class from notebook Cell 13 |
| P10 | AI Integration (FastAPI Microservice) | Stand up the real FastAPI app with /dlp/scan, /audio/analyze, /risk/evaluate — the notebook's own comment notes the original version was 'just a class, no app, no endpoints' and had to be fixed; verify the production port is genuinely reachable over HTTP, not just importable |
| P12 | End-to-End Integration | Confirm AI Integration (Phase 10) responses flow unmocked into the risk engine |
| P13 | Security + AI + Performance Testing | Final DLP recall/precision/FPR |
| P13 | Security + AI + Performance Testing | Go/no-go call on Phase 2 XGBoost+SHAP: only proceed if real analyst-labeled incident data (not notebook Cell 9's synthetic X_sim/y_sim) is actually sufficient — report the real corpus size before deciding, don't assume it in advance |
| P14 | Final Validation + Demo | Final measured-metrics summary compiled from evaluationResults |

### CS 1

| Phase | Phase Title | Task |
| --- | --- | --- |
| P0 | Foundation | Scaffold backend/, frontend/, ai-services/, data/, docs/, tests/, docker/ folders |
| P1 | Authentication + JWT + RBAC | Mongoose User/Role schemas + seed default roles |
| P1 | Authentication + JWT + RBAC | Auth routes: POST /api/v1/auth/register, /login, GET /auth/me |
| P2 | API Gateway + Security Middleware | Wire middleware order into the Express app entrypoint |
| P2 | API Gateway + Security Middleware | Request-logging hook (pre-cursor to Phase 5 audit logging, not the audit log itself) |
| P3 | DLP (Regex + Presidio + spaCy) | Internal dlpClient.js to call the DLP microservice from the Node backend |
| P4 | Reversible Encrypted Token Mapping (Redaction) | tokenMappings Mongoose schema with TTL index |
| P5 | Policy Engine + Audit Logging | policies and auditLogs Mongoose collections |
| P6 | Phase 1 Rule-Based Risk Engine | Internal risk-evaluation endpoint plumbing |
| P10 | AI Integration (FastAPI Microservice) | Node backend Security Engine layer calling the FastAPI service over the internal Docker network |
| P12 | End-to-End Integration | Replace every mocked frontend/backend call with the real service call |
| P12 | End-to-End Integration | End-to-end wiring across Express routes |
| P13 | Security + AI + Performance Testing | Wall-clock latency measurement per pipeline stage and end-to-end, per notebook Cell 11's benchmarking structure |
| P13 | Security + AI + Performance Testing | Load-test harness for the latency measurement |
| P14 | Final Validation + Demo | Rehearsed demo script covering the benign / spoofed-voice / social-engineering / DLP-leak / combined-incident scenarios |

### CS 2

| Phase | Phase Title | Task |
| --- | --- | --- |
| P0 | Foundation | Configure linting/formatting (ESLint/Prettier for JS, black/flake8 for Python) |
| P0 | Foundation | Set up docker-compose skeleton (empty service stubs) |
| P1 | Authentication + JWT + RBAC | React login/register screens wired to the auth API |
| P5 | Policy Engine + Audit Logging | Admin UI stub for policy configuration |
| P11 | Security Dashboard | Role-aware routing (Employee vs Analyst vs Administrator views) |
| P11 | Security Dashboard | Dashboard components consuming audit log / incident / evaluationResults data |
| P11 | Security Dashboard | Enforce the 'No measured data available' fallback at the component level |

# 10. Phase Dependency Graph

Linear backbone P0 -> P1 -> P2 with parallel tracks feeding P6 and P10:

- P0 (Foundation) -> P1 (Auth/RBAC) -> P2 (Gateway) -> P3 (DLP) -> P4 (Redaction) -> P5 (Policy/Audit) -> P6 (Risk Engine, Phase 1)

- P0 (Foundation) -> P7 (Faster-Whisper)  [parallel track, no backend dependency]

- P0 (Foundation) -> P8 (RawNet2)  [parallel track, no backend dependency]

- P7 (Whisper) -> P9 (mBERT + head)  [text input for live-audio path]

- P3, P4, P6, P7, P8, P9  -> P10 (AI Integration) — all six must be independently functional first

- P5 + P10 -> P11 (Security Dashboard)

- P1-P11 -> P12 (End-to-End Integration)

- P12 -> P13 (Security + AI + Performance Testing)

- P13 -> P14 (Final Validation + Demo)

# 11. API Ownership Matrix

| Endpoint | Owner | Phase | Type |
| --- | --- | --- | --- |
| POST /api/v1/auth/register, /login, GET /auth/me | Cyber 1 / CS 1 | 1 | Public |
| Gateway middleware (wraps all routes) | Cyber 1 / Cyber 4 | 2 | N/A (middleware) |
| POST /dlp/scan | Cyber 2 / AI 4 | 3 | Internal |
| POST /dlp/restore | Cyber 2 / AI 4 | 4 | Internal |
| POST /internal/audit/log | Cyber 4 / CS 1 | 5 | Internal |
| POST /internal/risk/evaluate | Cyber 3 / CS 1 | 6 | Internal |
| POST /audio/transcribe | AI 2 | 7 | Internal |
| POST /audio/analyze-deepfake | AI 1 | 8 | Internal |
| POST /nlp/classify | AI 3 | 9 | Internal |
| POST /dlp/scan, /audio/analyze, /risk/evaluate (consolidated gateway) | AI 4 / CS 1 | 10 | Internal |
| GET /api/v1/incidents, /audit-logs, /metrics | CS 2 / Cyber 4 | 11 | Public (role-restricted) |

# 12. Database Ownership Matrix

| Collection | Owner | Phase | TTL? |
| --- | --- | --- | --- |
| users | Cyber 1 / CS 1 | 1 | No |
| roles | Cyber 1 / CS 1 | 1 | No |
| tokenMappings | Cyber 2 | 4 | Yes — mandatory |
| policies | Cyber 3 / CS 1 | 5 | No |
| auditLogs | Cyber 4 / CS 1 | 5 | No (append-only) |
| incidents | Cyber 3 | 6 | No |
| evaluationResults | AI 4 | 13 | No |

# 13. Testing Ownership Matrix

| Test Area | Owner | Phase(s) |
| --- | --- | --- |
| Auth/RBAC test cases | Cyber 1 | 1 |
| Gateway/rate-limit/validation tests | Cyber 1 / Cyber 4 | 2 |
| DLP recall/precision/FPR | AI 4 | 3, 13 |
| Redaction round-trip / TTL | Cyber 2 | 4 |
| Policy/audit integrity tests | Cyber 4 | 5 |
| Risk-fusion combined-incident scenarios | Cyber 3 | 6, 12 |
| Whisper transcription smoke test | AI 2 | 7 |
| RawNet2 EER/ROC-AUC (real ASVspoof) | AI 1 | 8, 13 |
| mBERT per-label precision/recall/F1 | AI 3 | 9, 13 |
| AI Integration live-HTTP tests | AI 4 / CS 1 | 10 |
| Dashboard role-visibility / fallback tests | CS 2 | 11 |
| End-to-end scenario re-run | CS 1 (all teams) | 12 |
| Formal security test suite (OWASP-LLM01-aligned) | Cyber 4 | 13 |
| Latency/performance benchmark | CS 1 | 13 |
| Final rehearsal | All teams | 14 |

# 14. Integration Checklist

- Every AI service (RawNet2, Whisper, mBERT+head, DLP) verified independently functional before Phase 10 wiring begins

- AI services reachable only on the internal Docker network, never exposed externally

- Risk Engine weights/thresholds signed off by the team/supervisor before Phase 6 is marked done

- Audit log write path verified append-only (no delete route) before Phase 5 is marked done

- Token-mapping TTL index verified active before Phase 4 is marked done

- Dashboard 'No measured data available' fallback verified for every metric before Phase 11 is marked done

- All mocked responses replaced with live service calls before Phase 12 is marked done

- Every AI evaluation number traceable to a real run (not simulated/synthetic) before Phase 13 is marked done

- Documentation (docs/) matches actually-built system, with any gap labeled Future Work, before Phase 14 is marked done

# 15. Definition of Done (Global)

A task is complete only when all seven steps below have occurred, in order, for that task:

- IMPLEMENT — code/config written

- RUN — actually executed, not just reviewed

- TEST — against the phase's documented test cases

- FIX — issues found in TEST are resolved

- VERIFY — a second team member confirms the fix

- DOCUMENT — README/docs/ updated to match reality

- COMMIT — merged to develop via a reviewed feature branch

# 16. Risk Register

| Risk | Impact | Mitigation | Phase(s) |
| --- | --- | --- | --- |
| Missing AI Subsystem Proposal & SRS v2.1 — some implementation-level specifics unverified | Medium | Re-check Phases 7-10 once the document is supplied | 7-10 |
| Notebook's Phase 1 risk weights/threshold are not academically approved | Medium | Explicit sign-off required before Phase 6 is marked done | 6 |
| mBERT classifier trained on SMS-spam-derived proxy labels, domain gap vs. real call transcripts | Medium-High | Documented limitation carried into the final report, not hidden | 9, 13 |
| No GPU confirmed available | Medium | CPU-fallback path is a hard acceptance criterion for every model service | 7, 8, 9 |
| Notebook's XGBoost/synthetic-incident data is circular and not usable as-is | Medium | Phase 2 go/no-go explicitly gated on real analyst-labeled data at Phase 13 | 13 |
| Team-generated synthetic labeled data may be too small for meaningful evaluation | Medium | Actual corpus size reported at the end of labeling, not assumed in advance | 9, 13 |
| Integration risk concentrated at the single end-to-end wiring phase | High | Feature freeze around Phase 12; all-hands on integration bugs | 12 |
| Documentation drift from Chapter 1's aspirational baseline vs. what is actually built | Medium | Named documentation-accuracy owner at Phase 14; every claim traced to code or Future Work | 14 |

# 17. Future Work Separation

The following do not appear in any phase above and must be explicitly rejected if raised during implementation:

- Image/video deepfake detection

- Production PBX / enterprise telephony integration

- Universal HTTPS interception

- External Threat Intelligence module

- Voiceprint enrollment / speaker verification

- Federated learning / on-device deployment

- Autoencoder anomaly detection

Conditional items (XGBoost+SHAP, browser extension, SIEM export, confidence calibration) are distinct from Future Work: they are permitted but gated on explicit go/no-go decisions documented in Phase 13 and Phase 14, not automatically scheduled.

# 18. Closing Note

This document does not modify EASP_fixed.ipynb, the Chapter 1 Final v2.0 report, or the prior Readiness Audit. It is a planning and ownership artifact. Phase 1 and beyond do not begin automatically on the strength of this document — team/supervisor confirmation of the Open Decisions noted in Sections 4 and 16 is the next step.